## Slide 1: PHE’s Prescribed Medicines Review: 2nd update for the APPG PDD – 17 October 2018
17th October 2018

## Slide 2: The review will bring together the best available evidence on:
prevalence and prescribing patterns
the nature and factors that contribute to risk of dependence, and withdrawal or discontinuation symptoms among some people who take these medicines
effective prevention and treatment of dependence, withdrawal or discontinuation symptoms for each drug category

## Slide 3: Progress
Data analysis plan has been developed further, ERG membership have commented, plan now being finalised. First tranche of data has been received from NHS BSA.
A Rapid Evidence Assessment (REA) has been commissioned externally via an open tendering process to review the existing evidence. Expert Reference Group (ERG) members commented on the specification. RCP (Royal College of Physicians) National Guideline Centre (NGC) is undertaking the REA. ERG members have commented on the REA search protocols. Protocols will be published online using Prospero.
PHE project team are working closely with RCP and monitoring progress.
RCP NGC are undertaking a Call for Evidence as part of the REA. This is current and closes on 23rd October, to cover evidence on service models and papers that summarise patients’ experience.

## Slide 4: Further progress -
For transparency, information about the review has been posted on the .gov.uk website collection page set up specifically for the review. This includes scope, ERG membership & Declarations of Interest, ERG meeting notes
Note there have been ERG membership issues to be managed since the last APPG meeting along with similar peripheral issues that have taken time and energy
Next ERG meeting has been scheduled for January 14th 2019, at which we will present some early findings.

## Slide 5: Timeline*
September to December Rapid Evidence Assessment
September to October Call for evidence
October – January 2019 Data analysis
Organisation of peer review structure and timing
January 2019 ERG – Look at emerging findings
Feb – March report writing
Early Spring 2019 final ERG
Spring 2019 publish
*exact dates subject to variation

## Slide 6: Next steps
PHE team to work closely with RCP NGC to ensure progress on Rapid evidence Assessment
Data analysis initiation – NHS BSA closely supported by PHE evidence analysis team
Project progress and ERG papers to be published on .gov.uk website
Practical arrangements for ERG